## Sheet1
Phase | Task | What to Do | Command / Method
Preparation | Verify compatibility | Check OS, Java version, disk space, ports | Manual validation
| Document current configuration | Note ports, Endeca app name, Dgraph host, CAS ports | Review config files
| Stop Endeca services | Stop Workbench, CAS, Platform Services, MDEX | shutdown.sh or service scripts
Backup / Export | Export Workbench users | Export all users and roles | server/bin/workbench export-users users.xml
| Export Workbench site content | Export Experience Manager content and cartridges | Workbench UI → Admin → Export Site
| Backup Endeca application | Backup application directory | Copy /apps/<endeca_app>
| Backup pipeline configuration | Save Forge pipelines and scripts | /apps/<app>/config/pipeline
| Backup CAS configuration | Save CAS config and attribute settings | /apps/<app>/config/cas
| Backup MDEX configuration | Save Dgraph configuration | /apps/<app>/config/mdex
Install 11.4 Components | Install MDEX 11.4 | Install in new folder | Example /opt/endeca/mdex/11.4
| Install Platform Services 11.4 | Install new EAC services | /opt/endeca/platform/11.4
| Install Tools & Frameworks 11.4 | Install Workbench + EXM | /opt/endeca/tools/11.4
| Install CAS 11.4 | Install CAS in new directory | /opt/endeca/cas/11.4
Application Setup | Create Each Endeca Application.
| Copy configurations from 11.3.2 | Copy app folder to new environment | /apps/<app>
| Initialize services | Register application with platform services | initialize_services.sh
| Restore configurations | Restore mdex, pipeline, cas configs | Copy config directories
Restore Data | Import Workbench users | Import exported users | workbench import-users users.xml
| Import Workbench site | Restore EXM content | Workbench UI → Import Site
Index Rebuild | Run baseline update | Rebuild search index | baseline_update.sh
Startup | Start Endeca services | Start in order: MDEX → Platform → CAS → Workbench | startup.sh
Validation | Verify Dgraph | Confirm search engine running | Check port (usually 15000)
| Verify Workbench login | Confirm users and roles work | http://host:8006/workbench
| Test search queries | Run sample queries | Through ATG or query URL
| Check logs | Validate no errors | logs/ directories
Post Migration | Run full indexing | Validate full data load | baseline or partial update
| Monitor system | Check performance and errors | log monitoring